## Sheet1
| TT | Tom | GT | George | ST | Shane
04/10/16 - 11/10/16 | 3 | Pre Pitch Presentation Research | 6 | Make skeleton | 4 | Make match 3 mechanic
| 1 | Make Presentation
12/10/16 - 18/10/16 | 3 | Demographic Research, Ks2 History | 2 | Model Table and Tent | 3 | Fix the match 3 Game
| 1 | Make the Presentation | 1 | Model artifact (Shield) | 3 | Add artifact to match 3 game
| 2 | Hub Design | 1 | Texture Artifact
19/10/16 - 25/10/16 | 2 | Skeleton Mood Boards | 4 | New Skeleton Model | 3 | Get Artifact to fall
| 1 | Texture Skeleton | 1 | Rig Skeleton | 4 | Check at Start for Matches
| 1 | Design Plot Select | 1 | Design Animations
26/10/16 - 02/11/16 | 3 | Model Ground Tiles | 1 | Model Anglo Saxoon outfit for skeleton | 2 | Shield Score Change
| 2 | Texture Ground Tiles | 2 | Talking Animation for Skeleton | 1 | Check at Start for Matches
| 1 | Lock Camera to Map grid | 1 | Texture Outfit | 2 | Test On Mobile
| 1 | Menu System Design | 0.5 | Re Texture Shield
02/11/16 - 08/11/16 | 3 | Write out facts | 2 | Model a Crown | 3 | Comment Code
| 3 | Start Missing world mechanic | 1 | Re texture coin | 3 | Switch click to drag
| 3 | Build Menu | 2 | Model a wood cutting axe | 2 | Check matches at start
|  |  | 2 | Model a Cross
|  |  | 2 | Model a Tunic
09/11/16 - 15/11/16 | 4 | Continue missing word mechanic | 1 | Model a cauldron | 10 | Re start match 3 game
| 1 | Make a Presentation | 1 | Model a Plow
| 1 | Test Touch for Word Mechanic | 3 | Anglo Saxon Hut
| 4 | Assembly | 3 | Anglo Saxon church
|  |  | 3 | Anglo Saxon castle
16/11/16 - 22/11/16 |  | Menu Scroll |  | Portal |  | Clear on Match
|  | Code menu UI |  | Texture Stall |  | Lock movement
|  | Skeleton Menu Waypoiunt |  | Texture Plow |  | Scrore
|  | Trello |  | Model Norman Shield
| 40 |  | 40.5 |  | 40