## Sheet1
| TT | Tom | GT | George | ST | Shane
04/10/16 - 11/10/16 | 3 | Pre Pitch Presentation Research | 6 | Make skeleton | 4 | Make match 3 mechanic
| 1 | Make Presentation
12/10/16 - 18/10/16 | 3 | Demographic Research, Ks2 History | 2 | Model Table and Tent | 3 | Fix the match 3 Game
| 1 | Make the Presentation | 1 | Model artifact (Shield) | 3 | Add artifact to match 3 game
| 2 | Hub Design | 1 | Texture Artifact
19/10/16 - 25/10/16 | 2 | Skeleton Mood Boards | 4 | New Skeleton Model | 3 | Get Artifact to fall
| 1 | Texture Skeleton | 1 | Rig Skeleton | 4 | Check at Start for Matches
| 1 | Design Plot Select | 1 | Design Animations
26/10/16 - 02/11/16 | 3 | Model Ground Tiles | 1 | Model Anglo Saxoon outfit for skeleton | 2 | Shield Score Change
| 2 | Texture Ground Tiles | 2 | Talking Animation for Skeleton | 1 | Check at Start for Matches
| 1 | Lock Camera to Map grid | 1 | Texture Outfit | 2 | Test On Mobile
| 1 | Menu System Design | 0.5 | Re Texture Shield
02/11/16 - 08/11/16 | 3 | Write out facts | 2 | Model a Crown | 3 | Comment Code
| 3 | Start Missing world mechanic | 1 | Re texture coin | 3 | Switch click to drag
| 3 | Build Menu | 2 | Model a wood cutting axe | 2 | Check matches at start
|  |  | 2 | Model a Cross
|  |  | 2 | Model a Tunic
09/11/16 - 15/11/16 |  | Continue missing word mechanic |  | Model a cauldron |  | Re start match 3 game
|  | Make a Presentation |  | Model a Plow
|  | Test Touch for Word Mechanic |  | Anglo Saxon Hut
Anglo Saxon church
Anglo Saxon castle
| 30 |  | 29.5 |  | 30